## Redacted web version 2025
2025-2026 Annual Work Plan - TWG on Ending Childhood Statelessness (2/10/25)
Vision |  | End childhood statelessness
Mission |  | Working together to prevent and end childhood statelessness and to ensure stateless children can fully enjoy all their rights in international standards, notably the CRC
Axe 1: Global Activities
Output 1 | Lead | Activities and Tasks | Timeframe
1.1: Comprehensive international normative and policy framework on ending childhood statelessness widely known including useful knowledge products. | UNICEF | 1.1.1 Compile and disseminate committments at GRF on ending childhood statelessness | Done (see ppt introducing TWG)
| Institute on Statelessness and Inclusion | 1.1.2 Regular updates of CRC Committee and other treaty bodies on ending childhood statelessness | Ongoing
| Organization for Security and Co-operation in Europe (OSCE) High Commissioner on National Minorities (HCNM); UNHCR; Office for Democratic Institutions and Human Rights (ODIHR) | Guide Opening Doors for Children: Prevention of Childhood Statelessness - Good Practices in the OSCE Area - TWG can help disseminate | Done ( see the publication online here https://www.osce.org/odihr/593126 and the press release that goes with it here https://www.osce.org/hcnm/595333 )
| Global Alliance Secretariat | Development of knowledge hub including by theme such as ending childhood statelessness | Ongoing
1.2: Synergies with other TWG and regional hubs | UNICEF/Child Identity Protection (CHIP) | 1.2.1: Explore opportunities for joint activities with the TWG on Protecting the Rights of Stateless Persons | Bi-annual meetings
| UNICEF/CHIP | 1.2.2: Explore opportunities for joint activities with the TWG on Addressing Discrimination in Nationality Laws & Policies | Bi-annual meetings
1.3: Strengthening partnership with other key stakeholders in the field of childhood statelessness | UNICEF/CHIP | 1.3.1 :Develop a matrix (online google form) to keep abreast of ongoing research, publications and calendar of key events | Ongoing
| UNICEF / CHIP/ TWG members with Global Alliance Secretariat | 1.3.2: Engage with the CRC/CEDAW and other relevant treaty bodies on the right to identity (birth registration, name, nationality and family relations) to advance work on ending childhood statelessness | Ongoing
| UNICEF / CHIP/ TWG members with Global Alliance Secretariat | 1.3.3: Strengthen engagement with academics who are active in the area of childhood statelessness
| UNICEF / CHIP/ TWG members with Global Alliance Secretariat | 1.3.4: Engagement with other international assistance provided in the area of legal identity and connection with statelessness | Ongoing
| UNICEF | 1.3.5 Identify opportunities for synergies with ongoing work with UN Legal Identity Agenda | Ongoing
1.4 Strengthening the advocacy and external communication as TWG |  | 1.4.1 Update the TWG website | Q2-Q4 2025
| UNICEF / CHIP with Global Alliance Secretariat | 1.4.2 Development of a multi-year progress report as TWG | Q4 2025 - Q1 2026
| UNICEF / CHIP with Global Alliance Secretariat | 1.4.3: Initiate a webinar series of TWG work and/or social media campaign and/or short videos (e.g. Experts CHIP in series) | Ongoing
| UNICEF / CHIP with Global Alliance | 1.4.4: Development of a child friendly tool on access to justice for children lacking a birth certificate and/or stateless | 2026
Axe 2: Regional initiatives
Output 2 | Lead | Activities and Tasks | Timeframe
2.1 : Build Synergies with regional mechanisms | African Union (AU) | Dissemination and implementation of African Union Protocol on Rights on Specific Aspects of the Right to a Nationality and the Eradication of Statelessness in Africa - model law is being developed by Pan African Parliament. Regional consultations are scheduled mid-year. Input to this draft model law and online participation is possible. | Ongoing
| African Committee on Experts on Rights and Welfare of the Child (ACERWC) | Call for input on birth registration and digitalisation - can raise issue of discriminatory practices that can lead to statelessness | Ongoing
| ASEAN or the Economic and Social Commission for Asia and the Pacific (ESCAP) promotes cooperation among its 53 member States. | Regional Action Framework (RAF) for CRVS in Asia and the Pacific and the Asia-Pacific CRVS Decade 2015-2024 (ESCAP resolution 71/14) | Ongoing
| AMERICAS | Cartagena+40: Chile Declaration and Plan of Action 2024-2034 https://www.acnur.org/sites/default/files/2024-12/Chile_Declaration_and_Plan_of_Action_ENG.pdf | Ongoing
| Council of Europe (COE) | European Committee on Legal Co-operation (CDCJ) adopted a feasibility study for a non-binding legal instrument regarding stateless children’s access to nationality and agreed to revise Recommendation CM/Rec(2009)13 on the nationality of children to be complemented with a checklist for policy makers. The CDCJ also examined the draft compendium of good practices on access to nationality for stateless children and provided the necessary guidance for its completion in 2025. | Ongoing
| European Network on Statelessness (ENS) | Engage with European institutions and civil society to mainstream statelessness within relevant child rights frameworks, highlighting its intersectional nature and disproportionate impact on marginalised children. This will include engaging in policy discussions around the EU Child Rights Action Plan, EU Child Guarantee, EU Enlargement, EU Strategic Framework for Roma Equality, Inclusion, and Participation, and participating in the annual EU Child Rights Forum, as well as engaging with the European Parliament Intergroup on Children's Rights. It will also include engaging with relevant Council of Europe frameworks and initiatives including the CDCJ-MIG initiative on children's nationality and child-friendly procedures. We will also participate in civil society initiatives, including the Child Rights Action Group and Initiative for Children in Migration, to mainstream statelessness in their work. | Ongoing
| Organisation of Islamic Cooperation (OIC) |  | Ongoing
| Arab Declaration on belonging and legal identity | Adopted July 2024 - regional meeting | Ongoing
Axe 3: Country initiatives
Output 3 | Lead | Activities and Tasks | Timeframe
3.1: Technical support to country offices. | UNICEF/Child Identity Protection (CHIP) & TWG members | 3.1.1 Provide targeted technical advice and support at country level on activities related to ensuring every child’s right to a nationality. Specific areas of focus to be determined based on actual needs and requests for support related to the prevention and reduction of childhood statelessness. | Ongoing
Axe 4: Coordination and Programming Support
Output 4 | Lead | Activities and Tasks | Timeframe
4.1: TWG will operate with a regular coordination | Global Alliance Secretariat with UNICEF / CHIP | 4.1.1: Organize a quarterly TWG meeting to ensure inter-agency coordination and collaboration | ongoing
| Global Alliance Secretariat with UNICEF / CHIP | 4.1.2: Consider the role of co-chairs, Secretariat and TWG and agree on new formal ToRs | ongoing
| Global Alliance Secretariat with UNICEF / CHIP | 4.1.3 Strengthen resource mobilization effort with traditional donors, regional banks and foundations | ongoing